## Development Plane
E-Prescription
Module | Sub-Module | Task Item | Durations(Hours) | Phase-I | Buyer Comment
User Management | Create | Create/Register a User according basic fields | 4 | X
| Edit | Edit a registered user fields as per business | 4 | X
| Change Password | User can change his/her password | 3 | X
| Forgot Password | If user forgot password then he/she can apply for password recovery via registered phone no with OTP | 4 | X
| Profile | User can view Profile | 2 | X
X
Subscription | Create | Create subscription plan | 4 | X
| Update | Update subscription plan | 3 | X
| Delete |  |  | X
| History | View all Subscription | 2 | X
X
OTP Integration | Setup | OTP Integration Setup environments | 4 | X
| SMS Integration | Sending client mobile otp from our system | 4 | X
| Verify OTP | OTP Verify from given code by client | 4 | X
X
Prescription Management | Create | Create all prescription items | 4 | X
| Edit | Edit all prescription items | 3 | X
| Delete | Delete all prescription items | 2 | X
| History | View all prescription | 4 | X
X
Payments | Create | Create/Add amount | 4 | X
| Edit | Edit/Update amount | 2 | X
| History | View all payments | 2 | X
X
Admin | Examination | Create all examination items | 2 | X
|  | Edit all examination items | 2 | X
|  | Delete all examination items | 2 | X
| Medicine | Create all medicine items | 2 | X
|  | Edit all medicine items | 2 | X
|  | Delete all medicine items | 2 | X
| Users | View all Subscription | 2 | X
|  | Delete specific user | 2 | X
| Payments | View all payments | 2 | X
|  | Delete/Remove subscription plan | 2 | X
|  | Total Hours- | 79
|  | Expected Budget- | 102700